# Ovule Number & Reproductive Isolation — Task List

Email thread of 12 January 2026 (Maddie James, Kate Ostevik, Daniel Ortiz-Barrientos, Loren Rieseberg), with carried-over items from the October 2025 meeting..

## 1. Outstanding analyses

| Task | Owner | Status | Notes |
| --- | --- | --- | --- |
| Statistically grounded ovule threshold | Kate & Maddie; help from Daniel | To do | Replace the visual cut-off (100 ovules, log = 2) for the few-vs-many split with a data-driven method (e.g. a breakpoint or model-based threshold). Use Machine Learning to classify too; many new methods that excel at this. |
| Ovule number vs F1 fertility & viability | Kate & Maddie; help from Daniel | Paused | Analysis was halted once the ovule–RI signal weakened; revisit if the team chooses to keep pursuing ovule number. |
| Family-level analysis | Kate & Maddie; help from Daniel | To do | Not yet run on the new dataset, though it was done on the previous one. Justify in light of statistical approach and biology. |
| Diversification analysis | Daniel | Open | Daniel offered to spearhead this in October; confirm whether it is still going ahead and at what stage. |

## 2. Team decisions & coordination

| Task | Owner | Status | Notes |
| --- | --- | --- | --- |
| Whole-team meeting | All | To do | Discuss the weaker results and agree on direction; Kate and Maddie flagged this as the next step now that the data are final. |
| Daniel to explore the data | Daniel | To do | Independent look at the final datasets and code in the shared Drive folder. |
| Decide path given weaker results | All | Decision needed | The ovule–RI relationship is now marginal/non-significant; only genetic distance predicts RI. Consider merging the crossability dataset with Graeme’s work. |
| Read Graeme’s paper | All (esp. Kate & Maddie) | To do | Read the pollen-tube manuscript (paper #1) before advising on a journal. |
| Status of Graeme’s paper | Loren / Graeme | Open | Graeme is editing the pollen-tube chapter into a succinct, high-impact manuscript; confirm current state. |

## 3. Publication & manuscripts

| Task | Owner | Status | Notes |
| --- | --- | --- | --- |
| Choose submission target for Graeme’s paper | All | Decision needed | Graeme suggested PNAS first, then Current Biology, Nature Ecology & Evolution, or Proc. B. Decide after reading the draft. |
| Ovule-number references / draft of paper #1 | Graeme | Open | Outstanding from the October thread – references and a circulating draft. |
| Drive crossability work toward publication | All | Ongoing | Team intends to push the work to a publication over the coming months regardless of the final pattern. |

## Already completed

For context, the following are done and need no further action unless the team revisits the approach:

- Final datasets assembled – 110 phylogenetically independent crosses selected from 578 total, chosen to maximise species coverage while avoiding shared evolutionary history.

- Genetic distances computed for the phylogenetically independent crosses.

- PGLS pipeline running – base model (RI ~ ovule number, Brownian motion) and full model with all covariates (genetic distance, mating system, life history, RI measure).

- Ovule number tested as both a continuous and a categorical variable.

- RI-type subsets analysed (pollen competition and seed set).

- Asymmetrical (directional) RI tested – maternal ovule number as a predictor when each species was the female parent.

- Alternative evolutionary models compared via phylolm (Brownian, Ornstein–Uhlenbeck, lambda, delta, kappa).